## Sheet1
Task	Start Date	Duration (weeks)	End Date	Team Member
Complete BOM	11/01/17	2	17-Nov	Mark M.
Split comm and controls state diagrams	11/17/17	2	21-Nov	Kirk Jungles
Spec out Application	11/17/17	2	24-Nov	Georges
Spec out Microcontroller	11/17/17	2	24-Nov	Amanda
Pick an analog to digital converter	11/17/17	2	24-Nov	Arman, Peter
Get started with Marionette	11/17/17	2	24-Nov	Chuck, Mark
Program for LOX valve servo	11/		8-Dec	Peter, Arman